## Backlog
ID | User Story / Task | Category (SDLC Phase) | Priority (MoSCoW) | Estimate (Story Points) | Planned Day
PL-01 | Define product vision and goals | Planning | Must | 3 | Day 1
PL-02 | Write README.md with original vision | Planning | Must | 2 | Day 1
PL-03 | Document user stories | Requirement Analysis | Must | 3 | Day 1
PL-04 | Create Use Case Diagram | Requirement Analysis | Should | 2 | Day 1
PL-05 | Write Use Case Descriptions | Requirement Analysis | Should | 2 | Day 1
PL-06 | Create Business Function Diagram (BFD) | Requirement Analysis | Should | 2 | Day 1
DS-01 | Design system architecture (Clean + Monolith) | System Design | Must | 3 | Day 2
DS-02 | Draw ERD | System Design | Must | 3 | Day 2
DS-03 | Draw Class and Sequence Diagrams | System Design | Should | 2 | Day 2
DS-04 | Create BRD, FRD, NFR | System Design | Should | 3 | Day 2
DS-05 | Draw UI Wireframes | System Design | Should | 2 | Day 2
IM-01 | Setup frontend/backend structure | Implementation | Must | 3 | Day 3
IM-02 | Implement Auth API | Implementation | Must | 3 | Day 3
IM-03 | Create DB migration scripts | Implementation | Must | 2 | Day 3
TUT-01 | Build tutorial list/detail UI | Implementation | Must | 3 | Day 4
TUT-02 | Create CRUD API for tutorial content | Implementation | Must | 3 | Day 4
TUT-03 | Implement discovery point system | Implementation | Should | 2 | Day 4
EX-01 | Integrate Monaco/CodeMirror editor | Implementation | Must | 3 | Day 5
EX-02 | Create Exercise + Submission DB models | Implementation | Must | 2 | Day 5
EX-03 | Build code evaluation service | Implementation | Must | 3 | Day 5
RMP-01 | Implement roadmap tracking and EXP gain | Implementation | Must | 3 | Day 6
RMP-02 | UI for progress tracking | Implementation | Should | 2 | Day 6
QA-01 | Write manual/auto test cases | Testing | Must | 2 | Day 6
QA-02 | Log bugs found | Testing | Must | 1 | Day 6
DEP-01 | Deploy to VPS or Vercel | Deployment | Must | 3 | Day 7
DEP-02 | Write user guide and install guide | Deployment | Must | 2 | Day 7
DEP-03 | Document API (Swagger/Markdown) | Deployment | Must | 2 | Day 7
DEP-04 | Write final QA report | Testing | Should | 2 | Day 7

## DescriptionCode
Code | Description
PL-01 | Define project vision and scope
PL-02 | Write README.md with tech stack and overview
PL-03 | Define user personas and journey map
PL-04 | Write User Stories for all features
PL-05 | Draft initial Sprint Plan and timeline
PL-06 | Create Use Case Diagram and BFD
DS-01 | Write BRD (Business Requirement Document)
DS-02 | Write FRD (Functional Requirement Document)
DS-03 | Create ERD for core entities
DS-04 | Create UML diagrams: Class, Sequence
DS-05 | Design UI Wireframes
IM-01 | Initialize project repo and structure
IM-02 | Setup authentication (login/register/profile)
IM-03 | Setup database migration and seed
TUT-01 | Create tutorial topic list UI
TUT-02 | Create tutorial detail and navigation
TUT-03 | Integrate tutorial backend API
EX-01 | Integrate code editor UI (e.g., Monaco)
EX-02 | Setup backend code evaluation service
EX-03 | Save and show submission result
RMP-01 | Roadmap selection and join flow
RMP-02 | Track roadmap progress and unlock logic
QA-01 | Write test cases and checklist
QA-02 | Conduct manual tests and fix bugs
DEP-01 | Setup deployment pipeline (Docker)
DEP-02 | Deploy to VPS or platform (e.g., Render)
DEP-03 | Write UserGuide and InstallationGuide
DEP-04 | Write API Documentation and Final Report